## Slide 1: RUSA Review Meeting Presentation for Eastern & Central Zone

## Slide 2: Overview of RUSA Journey
1. Coverage Goals
As on date, 29 states and 6 UTs have responded to participate in RUSA. A total of 1513 institutions have been supported so far, which is 41% of the total institutions to be supported during this plan period ending 31st March 2017.
2. Gross Enrollment Ratio (GER)
The National GER prior to the launch of RUSA was 20.8 (2012), with Male GER at 22.1 and Female GER at 19.4. The GER is now at 22.6 (2014) with Male GER- 23.7 and Female GER at 21.4, indicating robust increase in GER and moving rapidly towards the national target of 25 by 2017. The SC GER overall has improved significantly from 14.9 (2012) to 17.4 (2014), while the ST GER has also increased slightly from 11(2012) to 12 (2014)
3. Student- Teacher Ratio
It is quite remarkable to see that the STR (2012), which was at 24:1 has actually progressed well and it currently at 20:1 (2014) inching closer to the global average (14:1).
4. Amount Approved and released
The total amount approved under RUSA till now is Rs. 7932 cr and amount released so far is Rs. 1193 cr.

## Slide 3: Agenda Items for Zonal Review
1. Feedback on RUSA Handbook
2. State's participation on Public Finance Management System (PFMS)
3. Review of performance of States under RUSA vis-a-vis following:
Physical and Financial achievements (component-wise)
Progress on Reform Agenda
Status of utilization of Preparatory Grants, MMER , Model Degree College funds etc
Submission of photographs on physical progress(component-wise)
4. States’ participation in Higher Education Leadership Forum
5. Status of Detailed Project Reports- submission of all relevant documents and fund
release till date
6. Research and Innovation Plans of States
7. Progress of Accreditation reforms (NAAC ) in the State
8. GIS Mapping of all the institutions sanctioned under RUSA
9. State’s Evaluation Assessment Framework
10. Any other item

## Slide 4: Action on Prerequisites Institutional structure
State of the Zone | Formation of SPD | Formation of SHEC | Formation of TSG | No. of meetings of SHEC
Andaman & Nicobar Islands | Functional | Dec-2013 (executive order) | Not Notified | 3
Bihar | Functional | Formed by an Executive Order | Not in existence | Regular
Chhattisgarh | Functional | Executive Order Notified. Bill to be passed in the Legislative Assembly | Not in existence | 2
Jharkhand | Functional | Executive order. A Committee has been formed to draft the Act of SHEC. | Not notified | 2
Madhya Pradesh | Functional | Executive Order Notified. Bill to be passed in the Legislative Assembly | Not in existence | 2
Odisha | Functional | Executive Order Notified. Bill to be passed in the Legislative Assembly | Functional | 0
West Bengal | Functional | Act of State Legislature | Functional | Regular

## Slide 5: Action on Prerequisites Financial compliance
State | % of GSDP on HE 2013-14 (2014-15) | Transactions of Funds through RUSA bank account for all components | Central Share (In Rs. Cr) | State share (In Rs. Cr) | Amt transferred to Institutions
Andaman & Nicobar Islands | Not Reported | Yes (pending revalidation) | Yes | Yes | Yes
Bihar | 1.5% (2014-15) and 1.33% in 2013-14 | Yes | Yes | No | No
Chattisgarh | Yes; 2013-14:- 0.463 % ; 2014-15 :- 0.585 %; | Yes | Yes | Yes | Yes
Jharkhand | 0.42% in 2013-14 | Yes | Yes | Yes | No
Madhya Pradesh | 0.29% (HE) + 0.06 (TE) = 0.35% (2012-13) | Yes | Yes | Yes | Yes
Odisha | 0.56% for 2013-14 0.59% for 2014-15 | Yes | Yes | Yes | Yes
West Bengal | 0.3412% for 2014-15 | Yes | Yes | Yes | Yes

## Slide 6: Action on Prerequisites Accreditation Reforms
State of the Zone | Accreditation % of Public Funded Institutions
Andaman & Nicobar Islands | No Accreditation
Bihar | Below 50%
Chhattisgarh | Over 90%
Jharkhand | 75- 89%
Madhya Pradesh | Below 50%
Odisha | 75-83%
West Bengal | 70%

## Slide 7: Action on Prerequisites Governance Reforms
State of the Zone | Governance Reforms
Andaman & Nicobar Islands | Not Applicable
Bihar | Initiated audit of Universities, Set up pay verification cell. State is introducing Financial Management System (FMIS). Search Committee system introduced for appointments of the Vice Chancellors and Pro VCs. Committees have been formed on Academic Reforms, NAAC Accreditation, MIS & ICT.
Chhattisgarh | All State Universities have Board of Governors, Board of Studies, Academic Council and Finance Committee .
Jharkhand | State has constituted a Committee vide letter dated 09.10.2015 to draft the SHEC Act. Jharkhand has Single University Act for entire state. The University Act is under process of Amendment since 2013.
Madhya Pradesh | Vishwavidyalaya Adhiniyam 1973 for 6 Conventional Universities. Separate Act for other Universities
Odisha | Vice Chancellor's Conclave; State institutions have Boards of Governors/Syndicates; Students advisory cells, Internal Quality cells.
West Bengal | SHEC Act 2015 enacted to fine tune the functioning of SHEC functional from 1994. Power of appointing Teaching / non Teaching Staff & officers of university lies with the V.C subject to approval of the Executive Council.

## Slide 8: Action on Prerequisites Affiliation Reforms
State of the Zone | Affiliation Reforms
Andaman & Nicobar Islands | Not Applicable
Bihar | Only Magadh University has more than 100 affiliated Colleges. All other universities have less than 100 affiliated colleges. Patna University has no affiliated College under it.
Chhattisgarh | Durg University, Durg has been created in the current session i.e. in 2015 as State University through an Act. 118 colleges will be affiliated to this university.
Jharkhand | The State has laid the foundation for Technical University and Raksha Shakti University. The Technical university would affiliate all the technical colleges and would reduce the burden on other universities. There is also a proposal of the State to open a Koyalachal University.
Madhya Pradesh | 216 colleges/university and 388 colleges/university (Technical)
Odisha | For Universities imparting General education, on an average, there are 108 colleges affiliated to a university. Under RUSA, the State has been sanctioned 2 Universities: one by up gradation of an autonomous college and a cluster university. Both the Universities would be affiliating in nature, lessening the burden from the existing universities.
West Bengal | The average no. of colleges affiliated per university as on May 2015 under Higher Education Department (prior to the 2015-16 academic session) has come down to 56

## Slide 9
Status of Preparatory Grants
Name of State | Funds Released by Centre (In Rs. cr) | State Share Released by State (In Rs. cr) | Amount Utilized (In Rs. cr) | Current Status
Andaman & Nicobar Islands | 1.95 | 0 | 0 | Pending revalidation
Bihar | 2.6 | 1.4 | 2.9 | UC submitted
Chhattisgarh | 2.6 | 1.4 | 2.34 | UC submitted
Jharkhand | 1.95 | 1.05 | 0.27 | UC submitted
Madhya Pradesh | 3.25 | 1.75 | 1.91 | UC submitted
Odisha | 2.6 | 1.4 | 1 | UC submitted
West Bengal | 2.6 | 1.4 | 1.79 | UC submitted

## Slide 10: Creation of Universities by way of upgradation of existing autonomous colleges
Name of State | No. of Colleges | Name of Colleges | Funds Approved | Funds Released | Amount Utilized | Current Status
Andaman & Nicobar Islands | - | - | - | - | - | -
Bihar | - | - | - | - | - | -
Chhattisgarh | - | - | - | - | - | -
Jharkhand | 1 | Ranchi College, Ranchi | 55 | 0 | 0 | DPR not submitted by the State. State has informed that DPR has been prepared and sent to engineering cell for technical sanction.
Madhya Pradesh | 1 | Pt. SN Shukla Govt PG College | 55 | 0 | 0 | Revised DPR to be submitted by the State
Odisha | 2 | RD Women’s College, Bhubaneshwar GM College, Sambalpur | 110 | 0 | 0 | DPR processed for RD Women's College, DPR just submitted for GM College
West Bengal | - | - | - | - | - | -

## Slide 11
Creation of Universities by conversion of colleges in a Cluster
Name of State | No. of Colleges | Name of Colleges | Funds Approved | Funds Released | Amount Utilized | Current Status
Andaman & Nicobar Islands | - | - | - | - | - | -
Bihar | - | - | - | - | - | -
Chhattisgarh | - | - | - | - | - | -
Jharkhand | - | - | - | - | - | -
Madhya Pradesh | - | - | - | - | - | -
Odisha | 1 | Khalikote College- Lead College; SBRG College, Binayak Acharya College, Gopalpur College | 55 | 0 | 0 | Revised DPR submitted on 20th Jan, 2016
West Bengal | - | - | - | - | - | -

## Slide 12
Infrastructure grants to Universities
Name of State | No. of Universities | Funds Approved | Funds Released | Amount Utilized | Current Status
Andaman & Nicobar Islands | NA | 0 | 0 | 0 | 0
Bihar | 3 | 60 | 6 | 0 | UC not submitted
Chhattisgarh | 7 | 140 | 18.25 | 0 | UC not submitted. Released Rs 3.25 on 11.05.2015 and Rs. 12.5 crore on 30.09.2015
Jharkhand | 3 | 60 | 9 | 0 | UC not submitted. Released Rs. 7.5 crore on 30.09.2015 & Rs. 1.5 crore on 17.12. 2015
Madhya Pradesh | 3 | 60 | 4.875 | 0 | No UC has been submitted
Odisha | 9 | 180 | 53.125 | 8.125 | 2nd instalment released to 5 universities. UC for rest 4 awaited
West Bengal | 8 | 160 | 27 | 0 | UCs for 1st instalment awaited

## Slide 13
New Model Colleges (General)
Name of State | District | Funds Approved | Funds Released | Amount Utilized | Current Status
Andaman & Nicobar Islands | 1 (South Andaman) | 12 | 5.85 | 3.9 | pending revalidation
Bihar | 13 | 84 | 0 | 0 | 
Chhattisgarh | 5 (Raipur, Durg, Rajnandgaon, Kanker, Bastar) | 60 | 0 | 0 | Revised DPR to be submitted by the State
Jharkhand | - | - | - | - | -
Madhya Pradesh | 5 (Harda,Jhabua, Dindhori, Sheopur, Umaria) | 60 | 0 | 0 | Revised DPR to be submitted by the State
Odisha | 8 (Malkangiri, Boudh, Deogarh, Nayagarh, Nabarangpur, Naupada, Rayagada and Sonepur) | 96 | 31.2 | 16.3188 | State has provided 50% UC for MDCs
West Bengal | - | - | - | - | -

## Slide 14
Upgradation of existing degree colleges to model colleges
Name of State | No. of Colleges | Funds Approved | Funds Released | Amount Utilized | Current Status
Andaman & Nicobar Islands | 1 | 4 | 0 | 0 | DPR awaited
Bihar | 13 | 52 | 0 | 0 | Revised DPR awaited
Chhattisgarh | - | - | - | - | -
Jharkhand | - | - | - | - | -
Madhya Pradesh | 2 | 8 | 0 | 0 | Revised DPR to be submitted by the State
Odisha | 3 | 12 | 0.5 | 0 | Funds released for 1 College, DPR for rest 2 processed
West Bengal | - | - | - | - | -

## Slide 15
New Colleges (Professional)
Name of State | No. of Colleges | Name of District | Funds Approved | Funds Released | Amount Utilized | Current Status
Andaman & Nicobar Islands | 1 | South Andaman | 26 | 0 | 0 | DPR awaited
Bihar | - | - | - | - | - | -
Chhattisgarh | - | - | - | - | - | -
Jharkhand | 1 | East Singhbhum | 26 | 0 | 0 | DPR not submitted by State. State has informed that it is in the process of aquiring land.
Madhya Pradesh | 1 | Dhar | 26 | 7.8 | 0 | Funds have been released in December 2015
Odisha | - | - | - | - | - | -
West Bengal | 1 | 26 | 0 | 0 | 0 | 

## Slide 16
Infrastructure grants to colleges
Name of State | No. of Colleges | Funds Approved | Funds Released | Amount Utilized | Current Status
Andaman & Nicobar Islands | 3 | 6 | 0 | 0 | Processed for fund release
Bihar | 34 | 68 | 16.2 | 0 | 1st instalment released in Dec, 2015
Chhattisgarh | 54 | 108 | 12.48 | 0 | UC not submitted. Released Rs 4.385 on 11.05.2015 and Rs. 6.75 crore on 30.09.2015
Jharkhand | 30 | 60 | 9 | 0 | UC not submitted. Released Rs. 7.5 crore on 30.09.2015 & Rs. 1.5 crore on 17.12. 2015
Madhya Pradesh | 30 | 60 | 2.925 | 0 | UC not submitted.
Odisha | 115 | 230 | 47.3125 | 3.4125 | 2nd instalment released to 21 Colleges.
West Bengal | 82 | 164 | 35.3375 | 10.67 | UCs submitted for 34 colleges out of 58 colleges that have received 1st instalment

## Slide 17
Equity initiatives
Name of State | Funds Approved | Funds Released | Amount Utilized | Current Status*
Andaman & Nicobar Islands | 5 | 0 | 0 | DPR awaited
Bihar | 2.4 | 0 | 0 | Revised Proposal awaited
Chhattisgarh | 5 | 0.75 | 0 | UC not submitted. Fund released 17.12.2015
Jharkhand | 5 | 0.75 | 0 | UC not submitted. Released Rs. 0.625 crore on 30.09.2015 & Rs.0.125 crore on 17.12.2015
Madhya Pradesh | 0 | 0 | 0 | 
Odisha | 5 | 1.5 | 0 | 1st instalment released in December, 2015. Utilization underway
West Bengal | - | - | - | -
*Details of activities undertaken under Equity Initiatives should be furnished by the States,
especially targeted towards women and marginalized social groups